## Project Charter
Project Charter
Project Overview | Sauce and Spoon Project Proposal
Project name | Sauce & Spoon: Menu Tablets
Project Sponsor | Deanna (Director of Operations)
Project Manager | Peta : Project Manager
Expected Start date | 2024-04-01
Expected completion date | Pilot completion 1/7/2024 Project Completion 1/10/2024
Project Details
Opportunity statement | In our early years, Sauce & Spoon met revenue goals while maintaining quality. However, staff burnout led to high turnover. Now, despite sales growth, we face delays in service and flat profit margins. Our new initiative aims to improve efficiency and reduce errors
In scope and out of Scope | In-Scope: Set up services in the bar area for both locations. Control food waste by 25%. Reduce table turn time by 30 minutes Integrate the new system with the existing POS system. Out-of-Scope: Policy changes. Expanding services to all parts of the restaurant. Hiring more kitchen staff.
Project Goals | Install tablets in the bar area of two restaurant locations for immediate ordering and self-checkout. Track data points related to tablet usage, order speed, and guest satisfaction. Train staff effectively on tablet operation and integration. Enhance guest experience, reduce wait times, and increase sales of appetizers and specialty drinks. Aim to complete the installation and training within the next quarter.
Estimated Cost & Resources | Training materials & Fees = $10,000 Hardware & Software Implementation across locations = $30,000 Maintenance(IT fees through EOY) Updated website & Menu Design Fee = $5,000 Photography session w/ SharpFoto approved by Dianna & Omar = $500 Other Customization fees = =$550
Estimated Milestones | Piloting to being start of April and be implemented by end of June
Project Team | Project Sponsor: Deanna (Director of Operations) Project Stakeholder: Carter (Executive Chef) Project manager: Peta Project Stakeholder: Gilly (General Manager, North) Project Stakeholder: Alex (General Manager, Downtown) Project Stakeholder: Seydou (Restaurant Consultant)
Appendix | During Analysis look into need for increase in wages. Considering potential uplift in sales additional staff runners might be required. Suggestion was made that sourcing wages from Front of House department would be an option as we are predicting a decrease in wait time. Further analysis will need to be made before implementing any changes. How to measure kitchen staff satisfaction with the implementation of the Tablets?

## Stakeholder Analysis
Stakeholder Analysis
Stakeholder | Impact of Change | Level of Influence
Omar | 4 | 9
Deanna | 9 | 9
Carter | 4 | 7 | Chart axis | 5 | 5
Gilly | 7 | 8
Alex | 7 | 7
Nia | 2 | 2
Zane | 6 | 2
Larissa | 6 | 3
Seydou | 7 | 4

## Tasks and Timeline
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Tablet: (Phase 1.1)
Generate quotes and review costs | Inline with initial estimates | Week 1 Monday | Week 5 Tuesday* | 14* | Peta | bar: WEEK 1 M to WEEK 2 T; WEEK 4 M to WEEK 5 T
Source training material for POS system from Vendor | Ticketing, functions & admin over-rides - request via email | Week 1 Monday | Week 1 Wednesday | 3 | Peta | bar: WEEK 1 M to WEEK 1 W
Provide site blueprints to Vendor | Help intergrate service with table number/area | Week 1 Monday | Week 1 Monday | 1 | Gilly & Alex | bar: WEEK 1 M
Source contract and statement of work from Vendor | Pricing & terms and conditions | Week 3 Monday | Week 3 Friday | 5 | Seydou - Deanna Approve | bar: WEEK 3 M to WEEK 3 F
Coordinate tablets installation for bars | Shipping estimates 5-10 business days - testing tablet to arrive earlier | Week 1 Monday | Week 6 Thursday* | 10* | Seydou | bar: WEEK 1 M to WEEK 1 F
Planning (Phase 1.2)
Create a post-dining survey to assess customer satisfaction | 2 open ended questions and 5 closed end(2 single responce & 3 scaled) questions | Week 1 Thursday | Week 2 Monday | 3 | Peta | bar: WEEK 1 R to WEEK 2 M
Ensure internet connection is secure | Seydou will organise prior to installation across all sites | Week 2 Tuesday | Week 2 Tuesday | 1 | Seydou | bar: WEEK 2 T
Create POS marketing promoting the new business venture | Keep customers informed and excited for the launch - involve marketing | Week 2 Thursday | Week 3 Friday | 7 | Peta | bar: WEEK 2 R to WEEK 3 F
Create a behind-the-scenes video of the scratch-to-table process to show on the tablets |  | Week 10 Monday | Week 11 Friday | 10 | Peta | bar: WEEK 10 M to WEEK 11 F
Create a launch day plan: staffing, troubleshooting, etc. | Card payment security talking notes & new POS paring with current software | Week 3 Monday | Week 9 Friday | 15* | Peta - Approved by Dianna | bar: WEEK 3 M to WEEK 4 F; WEEK 9 M to WEEK 9 F
Organise photographer for marketing | Post on social media, use pictures on online menu | Week 2 Wednesday | Week 2 Friday | 3 | Peta | bar: WEEK 2 W to WEEK 2 F
Training (Phase 2)
staff communication to introduce the concept of the tablets | Ahead of training, motivate & get staff buy-in | Week 4 Monday | Week 4 Monday | 1 | Peta | bar: WEEK 4 M
Create a procedure for securing tablets at the end of the night (at the table or in a safe) | Prior to manager and staff training | Week 5 Monday | Week 5 Tuesday | 2 | Peta | bar: WEEK 5 M to WEEK 5 T
Create cleaning procedures | High contact surfaces - daily cleaning | Week 5 Wednesday | Week 5 Wednesday | 1 | Alex | bar: WEEK 5 W
Confirm testing tablet has arrived | Tablet will be used for training with training demo software provided by vendor | Week 5 Thursday | Week 5 Thursday | 1 | Seydou | bar: WEEK 5 R
Manager training | One day event | Week 6 Friday | Week 6 Friday | 1 | Peta | bar: WEEK 6 F
GM meeting with staff regarding buy-in | Gilly will plan this | Week 6 Friday | Week 6 Friday | 1 | Gilly | bar: WEEK 6 F
Waitstaff training planning | Using POS learning material from vendor, cleaning guide & EFT safety | Week 4 Friday | Week 5 Thursday | 5 | Peta | bar: WEEK 5 F to WEEK 6 R
Staff training day | Tablet training, cleaning, end of shift | Week 6 Thursday | Week 6 Friday | 2 | Gilly & Alex | bar: WEEK 6 R to WEEK 6 F
Tablet installation complete (Phase 3)
Schedule electrician to install of POS system and wiring | Seydou reach out to Vendors inhouse installer | Week 7 Monday | Week 8 Wednesday | 8 | Seydou | bar: WEEK 7 M to WEEK 8 W
Install working tablets in the bar area at the Downtown restaurant locations | Coordinate with Alex | Week 8 Thursday | Week 8 Thursday | 1 | Alex | bar: WEEK 8 R
Install working tablets in the bar area at the North restaurant locations | Coordinate wit Gilly | Week 8 Thursday | Week 8 Thursday | 1 | Gilly | bar: WEEK 8 R
Sync tablet software with POS | If required update software to latest iteration - Contact vendor to complete | Week 8 Friday | Week 8 Friday | 1 | Seydou | bar: WEEK 8 F
Launch Day (Phase 4)
Upload branding to tablets | Previously organised via marketing & coordinated with Vendor | Week 10 Monday | Week 10 Monday | 1 | Seydou - Peta Confirm | bar: WEEK 10 M
Upload menu's into the tablets | Previously organised with Carter | Week 10 Tuesday | Week 10 Tuesday | 1 | Seydou - Carter Confirm | bar: WEEK 10 T
Upload messaging about payment security on the tablets | Completed by Seydou approved by Deanna | Week 10 Wednesday | Week 10 Wednesday | 1 | Seydou - Peta confirm | bar: WEEK 10 W
implement a post-dining survey to assess customer satisfaction | Marketing assisting | Week 10 Wednesday | Week 10 Wednesday | 1 | Peta | bar: WEEK 10 W
Test run planning |  | Week 10 Thursday | Week 12 Wednesday | 10 | Peta | bar: WEEK 10 R to WEEK 12 W
Organise a mock practice run with friends and family of staff | training/troubleshooting in a comfortable environment | Week 12 Thursday | Week 12 Thursday | 1 | Dianna, Alex & Gilly | bar: WEEK 12 R
Launch day | One day event | Week 12 Friday | Week 12 Friday | 1 | Peta | bar: WEEK 12 F

## Survey Questions
Survey Questions
Quality Standards
Criteria- Category & Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type
Tablet ease of use/quicker ordering and check out | Do all the tablets work as expected? | Tablet navigation, ease of payment | How easy was it to find what you were looking for? Scale from 1 - 5 | Closed Ended
Tablet ease of use/Bringing down the average table turn time by 30 minutes | How quickly are customers learning how to navigate the tablets? | Time between being seated to ordering, amount of customer enquires to waitstaff | Did you find using the tablets a faster way to order? Scale from 1 -5 | Closed Ended
Customer satisfaction/Increase customer retention in tablet areas by 5% | Are customers having a better dining experience with the tablets? | Feedback from surveys and online reviews | Are the Tablets easy to use? | Closed Ended
Customer satisfaction/Increase customer retention in tablet areas by 5% | Are customers receiving the correct orders? | Kitchen receiving the correct orders from the tablets | Did you order anything incorrectly? Why so "provide answer here" | Open Ended
Effectiveness/Increase customer retention in tablet areas by 5% | Are the tablets functioning properly? | percentage of customers getting correct orders, | Did you encure any errors? If answer Yes, please explain. | Open Ended
Effectiveness/98% order accuracy | What is the success rate of the order ticketing | Kitchen receiving correct orders | N/A
Effectiveness/Bringing down the average table turn time by 30 minutes | What is the check out time of orders compared to traditional method? | Time between placing order and receiving | N/A
Productivity/Bringing down the average table turn time by 30 minutes | What is the percentage of customers reporting errors | tablet error log report coming back within variance range | N/A
Productivity/quicker ordering and check out | How are the staff engaging with the tablets? Are they able to resolve customer queries? Do they prefer to traditional method? | Feedback from internal surveys, staff retention, tablet engagement | If you had any issue with the tablets rate from 1 - 5 how staff were able to assist. | Close Ended
Productivity/Bringing down the average table turn time by 30 minutes | Is there a reduction of wait time for customers to be seated? | Bench mark of under 10 minutes | N/A
Productivity/Lobby wait time under 10 minutes | Which staff members are the best at training customers on the tablets? | Customer feedback, success rates, and training session observations | Do you remember the name of Staff member who assisted you? | Open Ended